National Wildlife Federations Eco-Schools USA Action Plan

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Pathway** | **Measure of Success** | **Time Frame** | **Responsible** | **Financial Costs** |
| **Energy**   1. Implement “Fancy Lunch” for all classrooms once a week throughout the month of October by 10/31/2016 where student eat with natural light and use cloth napkins along with trash free initiatives for lunch packaging 2. Children will make “turn of the light switch” reminders throughout the school 3. Reduce electricity use through appliance purchases throughout the school year | 1. 50% of classroom implement “Fancy Lunch” 2. Children will be able to understand the goal of energy conservation for creating signs 3. 100% of new appliance purchased will be Energy Star approved by December 2016 | 1. short term  2. short term  3. medium term | 1. Green Committee  2. Blue room and Yellow room children  3. Admin | 1. Will reduce electricity bill and help children to become more aware of energy conservation  2. None, all material are already provided in the classroom  3. Varies depending on appliance costs |
| **Healthy Schools**   1. Create a Physical Education Policy according to the Let’s Move initiative 2. Implement Physical Education Policy Use an eco-friendly cleaner for classroom | 1.Physical education policy will be create by 11/30/2016  2. Physical education policy will be implemented by 12/30/2016  3. 100% of classrooms will have new eco-friendly cleaner | 1.medium term  2.medium term  3.short term | 1. Let’s Move Committee  2. Let’s Move Committee and teachers  3. Admin | 1. None  2. None (except if new equipment/material bought)  3. cost of cleaners |
| **Sustainable Food**   1. Create a Healthy Snack Committee for faculty 2. Have a Healthy Snack Committee organize a once a month event for teachers to bring in ingredients for a salad buffet 3. Provide a salad bar snack for children once a month 4. Have a healthy eating signs/games in the classrooms | 1. At least 3 staff members will be on the committee  2. 50% of staff will participate  3. Salad bar snack for children will be available once a month beginning 11/1/2016  4. At least 50% of classrooms will have healthy eating signs/games in the classroom | 1. short term  2. long term  3. medium term  4. short term | 1. Vera  2. Healthy Snack Committee  3. Healthy Snack Committee  4. Admin and teachers | 1. none  2. personal costs from participants  3. Grocery costs for school  4. Cost of games bought |